## Fragen
Nr | ID | Lektion | Frage | Option A | A richtig? | Begründung A | Option B | B richtig? | Begründung B | Option C | C richtig? | Begründung C | Option D | D richtig? | Begründung D | Richtige Antwort | Begründung (richtig) | Antwortstatus | Quelle
1 | quiz:scaledagile/ai-native-safe-overview/final/001 | Lesson 1: AI-Native SAFe Overview | Which four shifts define the AI-Native upgrade to SAFe? | Full Automation of Delivery; Autonomous AI-Only Teams; Longer and More Stable Planning Cadences; Centralized Innovation Labs. | falsch | Incorrect. AI-Native SAFe keeps humans in the loop, keeps teams cross-functional and human-led, shortens cadences, and spreads innovation across the organization rather than centralizing it. | Focus on Outputs and Velocity; Specialist Silo Teams with AI Support; Annual Learning and Improvement Reviews; Innovation Restricted to Research and Development. | falsch | Incorrect. This is the opposite direction on every count: the shifts move away from output-centric management, silos, slow learning loops, and gatekept innovation. | Optimized for Outcome-Driven Flow; Cross-Functional, AI-Augmented Teams; Iterative Learning and Rapid Experimentation Cycles; Development and Innovation at Scale. | RICHTIG | Correct. These four shifts amplify the core Lean-Agile practices: outcomes gain intent, teams become AI-augmented, learning cycles gain rapid experimentation, and development at scale gains innovation at scale. | Prompt Engineering; Model Selection and Fine-Tuning; Token Economics; Agent Orchestration; Inference Cost Management. | falsch | Incorrect. These are AI techniques, not organizational shifts. The four shifts to become AI-Native describe how the operating model changes, not which tools get used. | Optimized for Outcome-Driven Flow; Cross-Functional, AI-Augmented Teams; Iterative Learning and Rapid Experimentation Cycles; Development and Innovation at Scale. | Correct. These four shifts amplify the core Lean-Agile practices: outcomes gain intent, teams become AI-augmented, learning cycles gain rapid experimentation, and development at scale gains innovation at scale. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0001
2 | quiz:scaledagile/ai-native-safe-overview/final/002 | Lesson 2: Optimized for Outcome-Driven Flow | With AI, a team triples its feature output this quarter. When is that work actually “done”? | When every one of the features has shipped all the way to production. | falsch | Incorrect. Shipping is an output event. With no evidence of changed customer or business value, an organization can optimize ever faster for the wrong thing. | When customer and business impact is validated and the learning is captured. | RICHTIG | Correct. AI removes the constraint on producing outputs, so shipping volume stops being the measure. Work is done when there is evidence the outcome moved, and the learning from that evidence is captured. | When the AI-generated code passes all of the automated tests and reviews. | falsch | Incorrect. Passing tests confirms the output works as specified: it says nothing about whether the work created the change in value it was meant to create. | When the team's velocity target is met and the burn-down chart reaches zero. | falsch | Incorrect. Velocity and burn-down measure volume delivered: exactly the output-driven measures that lose meaning once producing more is easy. | When customer and business impact is validated and the learning is captured. | Correct. AI removes the constraint on producing outputs, so shipping volume stops being the measure. Work is done when there is evidence the outcome moved, and the learning from that evidence is captured. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0002
3 | quiz:scaledagile/ai-native-safe-overview/final/003 | Lesson 5: Development and Innovation at Scale | A prompt tells an AI agent exactly what to build and how, yet the agent's proposals keep missing the point and ignoring organizational standards. Which pillars of direction are missing? | Specifications: the prompt simply needs more technical detail about what and how. | falsch | Incorrect. The what and how are already covered. More technical detail can't tell the agent why the work matters or which organizational standards apply: those are the intent and context pillars. | Access: the agent needs the permissions to deploy directly to production. | falsch | Incorrect. Deployment permissions don't help an agent understand why work exists or where it must fit, and keeping humans in the validation loop is a feature, not a limitation. | Intent (the why) and context (the organizational reality the work must fit). | RICHTIG | Correct. Directing AI reliably takes all three pillars connected: intent (why), specifications (what and how), and context (where). This prompt covers only specifications: without intent and context, the agent can't aim at the change being sought or fit the organization's standards. | Nothing is missing: the agent just needs a more capable underlying model. | falsch | Incorrect. A stronger model still can't infer the purpose behind the work or the organization's standards from a prompt that never provides them. | Intent (the why) and context (the organizational reality the work must fit). | Correct. Directing AI reliably takes all three pillars connected: intent (why), specifications (what and how), and context (where). This prompt covers only specifications: without intent and context, the agent can't aim at the change being sought or fit the organization's standards. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0003
4 | quiz:scaledagile/ai-native-safe-overview/final/004 | Lesson 3: Cross-Functional, AI-Augmented Teams | An AI-Native team gathers to decide together how it will split an upcoming outcome between its humans and its AI agents. In the team's Align-Sense-Respond rhythm, which interaction is that? | Sense: the team is gathering new information about its own workload and capacity. | falsch | Incorrect. Sense is the deliberate gathering and analysis of feedback and learning from multiple sources. This scenario is a decision being made, not feedback being analyzed. | Respond: any change to how the work is divided counts as a response. | falsch | Incorrect. Respond is the adjustment a team makes to workflows and products after sensing something. Here nothing was sensed: the team is making a forward-looking key decision, which is Align. | None of them: staffing decisions sit outside the team rhythm. | falsch | Incorrect. Deciding how humans and AI agents share the work is central to how an AI-Native team operates: it's a textbook Align moment. | Align: a key decision made together that moves the team toward the outcome. | RICHTIG | Correct. Align is where the team makes key decisions together so everyone, human and AI, moves in the same direction toward the outcome. Deciding how to split the work is exactly such a decision. | Align: a key decision made together that moves the team toward the outcome. | Correct. Align is where the team makes key decisions together so everyone, human and AI, moves in the same direction toward the outcome. Deciding how to split the work is exactly such a decision. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0004
5 | quiz:scaledagile/ai-native-safe-overview/final/005 | Lesson 3: Cross-Functional, AI-Augmented Teams | You're forming a new AI-Native team. What's the right way to describe what the team needs? | By headcount: AI-Native teams should be as large as possible to absorb AI's extra output. | falsch | Incorrect. The direction is the opposite: teams get smaller and nimbler because AI collaboration lets fewer people cover more capability. | By traditional role titles: one developer, one tester, one analyst, one designer per seat. | falsch | Incorrect. Fixed role-per-seat staffing is what the capability model replaces. Describing teams through the Product, Builder, Domain Expert, and AI capabilities keeps them small and flexible as AI absorbs more of the execution work. | By its four core capabilities: Product, Builder, Domain Expert, and AI. | RICHTIG | Correct. AI-Native teams are smaller, nimbler, and described through capabilities rather than fixed role titles: Product anchors the team in customer needs, Builder turns outcomes into working solutions, the Domain Expert makes solutions fit the organization, and AI provides data and automation at speed. | By AI agents first: humans are added only where agents fall short. | falsch | Incorrect. AI augments professionals rather than replacing them. Teams stay human-led: humans own the strategy, judgment, and domain expertise that direct what AI produces. | By its four core capabilities: Product, Builder, Domain Expert, and AI. | Correct. AI-Native teams are smaller, nimbler, and described through capabilities rather than fixed role titles: Product anchors the team in customer needs, Builder turns outcomes into working solutions, the Domain Expert makes solutions fit the organization, and AI provides data and automation at speed. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0005
6 | quiz:scaledagile/ai-native-safe-overview/final/006 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | AI compresses parts of the Plan-Do-Check-Adjust learning cycle. Which parts shrink, and what do teams do with the time they gain? | Plan and Adjust shrink: AI makes planning largely unnecessary, so teams simply build continuously. | falsch | Incorrect. It's the reverse: Plan and Adjust gain time and importance. AI speeds up doing and checking, which makes deliberate human planning and adaptive decisions more valuable, not less. | Do and Check shrink: teams reinvest the time in planning, adaptive decisions, and experiments. | RICHTIG | Correct. AI accelerates execution (Do) and validation (Check), so cadences compress and experimentation accelerates: teams spend the recovered time on Plan and Adjust, where human judgment matters most, and let evidence decide what happens next. | None of them shrink: AI adds review overhead that lengthens every phase of the cycle. | falsch | Incorrect. Human validation stays in the loop, but the net effect of AI is dramatically faster Do and Check phases: that's what makes rapid experimentation cycles possible. | All four phases shrink equally, so the cadences stay in the same proportion as before. | falsch | Incorrect. The compression is uneven: AI shortens Do and Check specifically, which is what frees teams to shift their attention toward Plan and Adjust. | Do and Check shrink: teams reinvest the time in planning, adaptive decisions, and experiments. | Correct. AI accelerates execution (Do) and validation (Check), so cadences compress and experimentation accelerates: teams spend the recovered time on Plan and Adjust, where human judgment matters most, and let evidence decide what happens next. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0006
7 | quiz:scaledagile/ai-native-safe-overview/final/007 | Lesson 5: Development and Innovation at Scale | When AI makes everyone in the organization a potential innovator, what keeps that innovation scalable and safe? | Restricting AI-powered building to the IT department, where it can be properly controlled. | falsch | Incorrect. Gatekeeping innovation back into one department gives up the shift's whole benefit. The answer to broad innovation is enablement with guardrails, not restriction. | Nothing: guardrails would only slow innovation down, defeating the whole purpose. | falsch | Incorrect. Ungoverned AI solutions create fragile systems and technical debt. Guidelines and governance are what let innovation scale safely: they're the enabler, not the brake. | Clear guidelines, shared AI infrastructure, and governance against fragile solutions. | RICHTIG | Correct. When employees across every department start building AI-powered tools, guidelines, shared infrastructure, and governance are what keep that innovation scalable, maintainable, and safe: without them, ungoverned solutions create fragile systems and technical debt. | A freeze on new AI tools until every existing solution is fully documented and audited. | falsch | Incorrect. A freeze halts the innovation the shift exists to unlock. Scalability comes from guidelines, shared infrastructure, and governance operating alongside innovation, not ahead of it. | Clear guidelines, shared AI infrastructure, and governance against fragile solutions. | Correct. When employees across every department start building AI-powered tools, guidelines, shared infrastructure, and governance are what keep that innovation scalable, maintainable, and safe: without them, ungoverned solutions create fragile systems and technical debt. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0007
8 | quiz:scaledagile/ai-native-safe-overview/final/008 | Lesson 1: AI-Native SAFe Overview | What does the AI-Native Professional combine? | Technical AI skills, fully replacing the human skills that AI has now commoditized. | falsch | Incorrect. AI commoditizes execution, not human skills. As it does, context, empathy, ethics, judgment, and strategy become more valuable, not less. | AI fluency (directing and evaluating AI) with human context, empathy, judgment, and strategy. | RICHTIG | Correct. The AI-Native Professional lives in the overlap of the two domains: AI handles tasks that don't require human judgment, and the professional directs the AI, not just its output, while applying the human skills that have become the organization's most important asset. | Deep expertise in one AI tool combined with certification in the organization's compliance standards. | falsch | Incorrect. Tools keep changing: what endures is AI fluency, knowing how to direct whatever AI comes next, paired with the human skills AI cannot supply. | Prompt-writing speed with the ability to approve AI output quickly enough to keep up the pace. | falsch | Incorrect. Approving output quickly is the opposite of the role: the AI-Native Professional critically evaluates AI output and stays accountable for it. | AI fluency (directing and evaluating AI) with human context, empathy, judgment, and strategy. | Correct. The AI-Native Professional lives in the overlap of the two domains: AI handles tasks that don't require human judgment, and the professional directs the AI, not just its output, while applying the human skills that have become the organization's most important asset. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0008
9 | quiz:scaledagile/ai-native-safe-overview/final/009 | Lesson 1: AI-Native SAFe Overview | Why is experimenting with AI no longer enough for an organization? | Experiments are too expensive to run at today's model prices. | falsch | Incorrect. Cost is not the reason. The problem is that isolated experiments do not change how the organization works. | Becoming AI-Native is a whole-organization way of working, not a set of pilots. | RICHTIG | Correct. The pace and scale of change demand more than isolated experiments. Unlocking value from AI takes a unified, organization-wide approach. | Most AI experiments fail for technical reasons. | falsch | Incorrect. The technology usually works. The gap is organizational, not technical. | Regulators now require organizations to move past the experimental stage. | falsch | Incorrect. No regulation drives this. The driver is the need to unlock real value from AI across the whole organization. | Becoming AI-Native is a whole-organization way of working, not a set of pilots. | Correct. The pace and scale of change demand more than isolated experiments. Unlocking value from AI takes a unified, organization-wide approach. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0009
10 | quiz:scaledagile/ai-native-safe-overview/final/010 | Lesson 1: AI-Native SAFe Overview | What does AI-Native SAFe provide to help organizations get a return from AI? | A catalog of approved AI tools and vendors. | falsch | Incorrect. AI-Native SAFe is an operating model, not a tool list. Tools change quickly, but the roles and structures endure. | The roles, processes, and structures needed to achieve a return from AI. | RICHTIG | Correct. Research found that the missing piece was a standard framework. AI-Native SAFe fills that gap with an outcome-driven operating model. | A guarantee that AI investments will pay off within one year. | falsch | Incorrect. No framework can guarantee returns. AI-Native SAFe provides the structure that makes returns achievable. | A dedicated AI department that runs all AI work centrally. | falsch | Incorrect. AI-Native SAFe spreads AI capability across the whole organization instead of centralizing it in one department. | The roles, processes, and structures needed to achieve a return from AI. | Correct. Research found that the missing piece was a standard framework. AI-Native SAFe fills that gap with an outcome-driven operating model. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0010
11 | quiz:scaledagile/ai-native-safe-overview/final/011 | Lesson 1: AI-Native SAFe Overview | Reviewing the AI-Native SAFe Big Picture, a colleague points to the portfolio level, where connected OKRs cascade from portfolio strategy and curated data keeps work at every level aligned to value. Which critical shift does this part of the Big Picture express? | Development at Scale to Development and Innovation at Scale | falsch | Incorrect. That shift is expressed by the AI Innovation Pipeline, whose shared platforms and embedded policies make innovation scalable across the organization. | Optimized for Flow to Optimized for Outcome-Driven Flow | RICHTIG | Correct. Connected OKRs, portfolio strategy, and curated data are the outcome-driven elements of the Big Picture. They keep everything flowing through the system aligned to value instead of output volume. | Iterative Learning Cycles to Iterative Learning and Rapid Experimentation Cycles | falsch | Incorrect. That shift appears in the cadenced events on the Big Picture, such as PI Outcome Planning and Sense and Respond, which shorten learning cycles across the ART. | Cross-Functional Teams to Cross-Functional, AI-Augmented Teams | falsch | Incorrect. That shift is expressed by the AI-Native ARTs and AI-Native Teams, smaller teams described through Product, Builder, Domain Expert, and AI capabilities. | Optimized for Flow to Optimized for Outcome-Driven Flow | Correct. Connected OKRs, portfolio strategy, and curated data are the outcome-driven elements of the Big Picture. They keep everything flowing through the system aligned to value instead of output volume. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0011
12 | quiz:scaledagile/ai-native-safe-overview/final/012 | Lesson 1: AI-Native SAFe Overview | In a human-centric AI culture, what becomes the organization's most important asset? | The size of its AI infrastructure budget. | falsch | Incorrect. Anyone can spend on infrastructure. The differentiator is the human judgment that directs what the AI produces. | Human skills such as creativity, empathy, and strategic decision-making. | RICHTIG | Correct. When AI handles the tasks that do not require human judgment, people are freed to direct outcomes. The ability to apply these human skills becomes the most important asset. | The number of AI agents deployed across its teams. | falsch | Incorrect. Agents are widely available. The value comes from the people who direct them well. | Exclusive contracts with the leading AI model providers. | falsch | Incorrect. Models are a commodity that any competitor can rent. Human skills are what cannot be copied. | Human skills such as creativity, empathy, and strategic decision-making. | Correct. When AI handles the tasks that do not require human judgment, people are freed to direct outcomes. The ability to apply these human skills becomes the most important asset. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0012
13 | quiz:scaledagile/ai-native-safe-overview/final/013 | Lesson 2: Optimized for Outcome-Driven Flow | In the outcome-driven product development cycle, what do measurements show? | How many outputs each team produced during the PI. | falsch | Incorrect. Counting outputs is output-driven measurement. The cycle measures progress toward outcomes instead. | Whether the outputs are making progress against the defined outcomes. | RICHTIG | Correct. Measurements provide the insight to change or keep the current plan. They connect the work back to the outcomes it was meant to move. | Which teams are working the fastest. | falsch | Incorrect. Speed of production stopped being the constraint once AI removed the output bottleneck. The question is whether the work is moving the outcome. | How much of the budget has been spent so far. | falsch | Incorrect. Spend tracking matters elsewhere, but measurements in this cycle show progress against outcomes. | Whether the outputs are making progress against the defined outcomes. | Correct. Measurements provide the insight to change or keep the current plan. They connect the work back to the outcomes it was meant to move. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0013
14 | quiz:scaledagile/ai-native-safe-overview/final/014 | Lesson 2: Optimized for Outcome-Driven Flow | Why must Portfolio Leadership include the organization's AI spend in its investment strategy? | AI costs are usage-driven, and consumption at scale can outrun a fixed budget. | RICHTIG | Correct. Costs shift from fixed salaries and licenses to variable consumption. Agents are paid in tokens, so usage must be modeled and managed. | AI vendors require an annual spending commitment before granting access. | falsch | Incorrect. Vendor terms are not the reason. The reason is that usage-driven costs behave differently from fixed costs. | AI spend is small enough to hide inside existing license budgets. | falsch | Incorrect. The opposite is true. A capability that costs little in pilot can become a major line item at scale. | Accounting rules require AI costs to be reported separately. | falsch | Incorrect. This is about investment strategy, not reporting rules. Usage-driven consumption changes how budgets must be planned. | AI costs are usage-driven, and consumption at scale can outrun a fixed budget. | Correct. Costs shift from fixed salaries and licenses to variable consumption. Agents are paid in tokens, so usage must be modeled and managed. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0014
15 | quiz:scaledagile/ai-native-safe-overview/final/015 | Lesson 2: Optimized for Outcome-Driven Flow | In AI-Native SAFe, where are OKRs used? | Only at the portfolio level, where strategy is set. | falsch | Incorrect. Portfolio OKRs alone leave teams disconnected from strategy. Every level writes outcomes relevant to its own work. | Only at the team level, where the work gets done. | falsch | Incorrect. Team OKRs need portfolio and ART outcomes above them to cascade from. Otherwise teams pull in different directions. | At every level, from portfolios to teams. | RICHTIG | Correct. AI-Native SAFe mandates OKRs at every level. Cascading outcomes keep ART and team work connected to strategy. | OKRs are optional and each ART decides whether to use them. | falsch | Incorrect. AI-Native SAFe now mandates OKRs at every level. They are how daily work connects to overall strategy. | At every level, from portfolios to teams. | Correct. AI-Native SAFe mandates OKRs at every level. Cascading outcomes keep ART and team work connected to strategy. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0015
16 | quiz:scaledagile/ai-native-safe-overview/final/016 | Lesson 2: Optimized for Outcome-Driven Flow | What is curated data? | Enterprise information deliberately prepared for AI. | RICHTIG | Correct. Curated data enables reliable and unique insights. Without it, AI produces fragmented or conflicting results. | Any data an organization stores in a database. | falsch | Incorrect. Storage alone is not curation. The data must be deliberately prepared so AI can use it well. | Data that has been anonymized for privacy compliance. | falsch | Incorrect. Anonymization is a privacy technique. Curation is about preparing data so it produces reliable insights. | Public data purchased from third-party providers. | falsch | Incorrect. Purchased data is available to competitors too. Curated proprietary data is the advantage no one else can copy. | Enterprise information deliberately prepared for AI. | Correct. Curated data enables reliable and unique insights. Without it, AI produces fragmented or conflicting results. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0016
17 | quiz:scaledagile/ai-native-safe-overview/final/017 | Lesson 2: Optimized for Outcome-Driven Flow | Data has been successfully curated when it meets which conditions? | It is complete, accurate, well-maintained, securely accessible, and clearly owned. | RICHTIG | Correct. These five conditions are what turn proprietary data into reliable raw material for AI. | It is stored in a single central warehouse with one global owner. | falsch | Incorrect. Curation is about the quality and stewardship of the data, not where it lives. Owners must be identifiable, but not singular. | It is fully structured, with all documents converted into tables. | falsch | Incorrect. Curation extends beyond structured records. Documents and slide decks hold much of an organization's knowledge and are prepared for AI too. | It is encrypted, backed up, and retained for at least seven years. | falsch | Incorrect. Those are IT practices, not the curation conditions. Curated data must also be complete, accurate, maintained, accessible, and owned. | It is complete, accurate, well-maintained, securely accessible, and clearly owned. | Correct. These five conditions are what turn proprietary data into reliable raw material for AI. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0017
18 | quiz:scaledagile/ai-native-safe-overview/final/018 | Lesson 3: Cross-Functional, AI-Augmented Teams | Teams on an AI-Native ART can move faster than ever. Why does the ART still keep a regular cadence? | Cadence builds in time to reconcile local decisions and dependencies before they accumulate. | RICHTIG | Correct. Cadence gives the organization the structure to metabolize the learning coming from fast-moving teams. It balances rapid innovation with cadence-based learning. | Cadence slows the teams down to a pace leadership can supervise. | falsch | Incorrect. Cadence is not a brake. It provides the structure that lets work move at the speed of AI safely. | Cadence is kept only for tradition, since the events no longer serve a purpose. | falsch | Incorrect. The events matter more at AI speed, not less. They are where local decisions get reconciled. | Cadence gives AI agents fixed deadlines to work toward. | falsch | Incorrect. Cadence exists for human alignment and learning, not for agent scheduling. | Cadence builds in time to reconcile local decisions and dependencies before they accumulate. | Correct. Cadence gives the organization the structure to metabolize the learning coming from fast-moving teams. It balances rapid innovation with cadence-based learning. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0018
19 | quiz:scaledagile/ai-native-safe-overview/final/019 | Lesson 3: Cross-Functional, AI-Augmented Teams | On an AI-Native Team, which capability brings the specialized customer and business context that makes solutions fit the organization? | Product | falsch | Incorrect. Product defines the vision and anchors the team in customer needs. The specialized domain context comes from the Domain Expert. | Builder | falsch | Incorrect. The Builder uses AI to turn outcomes into working solutions. The Domain Expert supplies the context those solutions must fit. | Domain Expert | RICHTIG | Correct. The Domain Expert brings deep customer, business, or regulatory knowledge. That context keeps solutions from staying generic. | AI | falsch | Incorrect. AI provides data and automation under human supervision. It cannot supply the organization's specialized business context. | Domain Expert | Correct. The Domain Expert brings deep customer, business, or regulatory knowledge. That context keeps solutions from staying generic. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0019
20 | quiz:scaledagile/ai-native-safe-overview/final/020 | Lesson 3: Cross-Functional, AI-Augmented Teams | What is the “POC Graveyard”? | The archive where retired AI models are stored. | falsch | Incorrect. The term is about failed adoption, not model storage. It names the pile of demos that never became real products. | Promising AI demonstrations that never reach scaled, sustained use. | RICHTIG | Correct. Most AI initiatives fail because no one owned the path from prototype to production. The AI Value Architect exists to fill that gap. | A list of AI vendors that went out of business. | falsch | Incorrect. The graveyard is inside organizations, not the vendor market. It holds proofs of concept that never scaled. | The backlog of AI ideas a team has not started yet. | falsch | Incorrect. These initiatives were started and even demonstrated. They died on the way from prototype to production. | Promising AI demonstrations that never reach scaled, sustained use. | Correct. Most AI initiatives fail because no one owned the path from prototype to production. The AI Value Architect exists to fill that gap. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0020
21 | quiz:scaledagile/ai-native-safe-overview/final/021 | Lesson 3: Cross-Functional, AI-Augmented Teams | Who is well positioned to become an AI Value Architect? | Outside specialists hired specifically for the role. | falsch | Incorrect. The AI Value Architect is not a new specialist hired from outside. It grows from existing roles. | Systems thinkers and coaches the organization already has, such as Scrum Masters, RTEs, and Architects. | RICHTIG | Correct. The role grows out of roles SAFe already has. People who already coach and hold the systems view can add AI fluency and step in. | The most senior AI engineer on each team. | falsch | Incorrect. Technical depth alone is not the qualification. The role needs coaching skill and a systems view across the ART. | Any volunteer, since the role needs no particular background. | falsch | Incorrect. The role draws on coaching experience and systems thinking. That is why existing SAFe roles are the natural candidates. | Systems thinkers and coaches the organization already has, such as Scrum Masters, RTEs, and Architects. | Correct. The role grows out of roles SAFe already has. People who already coach and hold the systems view can add AI fluency and step in. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0021
22 | quiz:scaledagile/ai-native-safe-overview/final/022 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What makes a product vision compelling in AI-Native SAFe? | It is informed by data, aligned with strategy, and anchored to architectural foundations. | RICHTIG | Correct. These three characteristics identify a compelling vision. A clear vision lets teams and AI agents make local decisions aligned to the long-term trajectory. | It is ambitious enough that no competitor could promise the same. | falsch | Incorrect. Ambition alone is not the test. The vision also needs data, strategy alignment, and architectural grounding. | It is written by leadership and kept stable for at least three years. | falsch | Incorrect. Who writes it and how long it lasts are not the defining traits. The three characteristics are data, strategy, and architecture. | It lists every feature the ART plans to build. | falsch | Incorrect. A feature list is a roadmap artifact, and an output-driven one at that. The vision defines the mission and long-term goals. | It is informed by data, aligned with strategy, and anchored to architectural foundations. | Correct. These three characteristics identify a compelling vision. A clear vision lets teams and AI agents make local decisions aligned to the long-term trajectory. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0022
23 | quiz:scaledagile/ai-native-safe-overview/final/023 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | On the Outcome-Driven Roadmap, what is a “moonshot”? | A milestone with an immovable external date. | falsch | Incorrect. That describes a fixed-date milestone. A moonshot is an outcome, not a milestone. | A bold, aspirational outcome that prioritizes innovation. | RICHTIG | Correct. A moonshot is a bold aspiration in its own outcome swimlane. Roofshots are the outcomes used to predictably optimize or iterate a product. | An outcome used to predictably optimize an existing product. | falsch | Incorrect. That is a roofshot. Moonshots prioritize innovation over predictability. | A release that reaches customers ahead of schedule. | falsch | Incorrect. Releases mark when value reaches customers. A moonshot is a type of ART outcome on the roadmap. | A bold, aspirational outcome that prioritizes innovation. | Correct. A moonshot is a bold aspiration in its own outcome swimlane. Roofshots are the outcomes used to predictably optimize or iterate a product. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0023
24 | quiz:scaledagile/ai-native-safe-overview/final/024 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What is the most significant logistical change in PI Outcome Planning compared to traditional PI Planning? | Only team leads attend, to keep the event small. | falsch | Incorrect. The entire ART attends. The change is the length, not the attendance. | The event is accomplished in a single day. | RICHTIG | Correct. PI Outcome Planning is a one-day event held at the start of every PI. The entire AI-Native ART attends. | The event is fully asynchronous, with no live sessions. | falsch | Incorrect. It is a live, facilitated day with breakouts, reviews, and a confidence vote. | It happens once a year instead of every PI. | falsch | Incorrect. It happens at the start of every PI. What changed is that it now fits in one day. | The event is accomplished in a single day. | Correct. PI Outcome Planning is a one-day event held at the start of every PI. The entire AI-Native ART attends. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0024
25 | quiz:scaledagile/ai-native-safe-overview/final/025 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Which two SAFe events does the Sense and Respond event replace? | PI Planning and the Solution Demo. | falsch | Incorrect. PI-level planning becomes PI Outcome Planning, a separate event. Sense and Respond replaces Inspect and Adapt and the System Demo. | Inspect and Adapt and the System Demo. | RICHTIG | Correct. Sense and Respond is a two-hour event at each iteration boundary. The first hour senses what happened, and the second hour decides what changes. | The Daily Stand-up and the Iteration Review. | falsch | Incorrect. Team-level rhythms continue through Align, Sense, Respond. The ART-level event replaces Inspect and Adapt and the System Demo. | Backlog Refinement and the Iteration Retrospective. | falsch | Incorrect. Those team practices are not what changed. Sense and Respond replaces the two ART-level learning events. | Inspect and Adapt and the System Demo. | Correct. Sense and Respond is a two-hour event at each iteration boundary. The first hour senses what happened, and the second hour decides what changes. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0025
26 | quiz:scaledagile/ai-native-safe-overview/final/026 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Early in development, a team wants honest reactions to a prototype from a small group of real customers. Which demo fits? | A personal, learning demo, such as a hand-picked focus group. | RICHTIG | Correct. This is the Test Hypotheses Before Scaling quadrant. Small audiences allow deeper interactions and repeated demos with the same group. | A broadcast, persuading demo, such as a launch event. | falsch | Incorrect. Launch events generate broad demand. That comes after the team has learned what works. | A personal, persuading demo for the biggest customer. | falsch | Incorrect. Persuading assumes the solution already works as intended. The team is still learning. | A broadcast, learning demo through self-guided product access. | falsch | Incorrect. Broadcast learning suits products already tested with a smaller group. This prototype has not reached that stage. | A personal, learning demo, such as a hand-picked focus group. | Correct. This is the Test Hypotheses Before Scaling quadrant. Small audiences allow deeper interactions and repeated demos with the same group. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0026
27 | quiz:scaledagile/ai-native-safe-overview/final/027 | Lesson 5: Development and Innovation at Scale | AI-Native SAFe defines two types of specifications. What are they? | Functionality specifications and policy specifications. | RICHTIG | Correct. Functionality specifications describe the intended implementation. Policy specifications set the limits the Builders must stay within. | Technical specifications and business specifications. | falsch | Incorrect. The split is not technical versus business. It is what to build versus the limits to build within. | Draft specifications and approved specifications. | falsch | Incorrect. Approval status is not the distinction. The two types are functionality and policy. | Human specifications and agent specifications. | falsch | Incorrect. Specifications serve people and agents alike. The two types are functionality and policy. | Functionality specifications and policy specifications. | Correct. Functionality specifications describe the intended implementation. Policy specifications set the limits the Builders must stay within. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0027
28 | quiz:scaledagile/ai-native-safe-overview/final/028 | Lesson 5: Development and Innovation at Scale | Which four work items does AI-Native SAFe recommend at a minimum on the AI Innovation Pipeline? | Epics, Capabilities, Features, and Stories. | falsch | Incorrect. That is the traditional SAFe requirements hierarchy. The pipeline's recommended set is Prototypes, Experiments, Features, and Enablers. | Prototypes, Experiments, Features, and Enablers. | RICHTIG | Correct. Teams are free to use more work items, but these four are the recommended minimum for managing work on the pipeline. | Tasks, Bugs, Spikes, and Releases. | falsch | Incorrect. Those are day-to-day tracking items. The recommended pipeline set is Prototypes, Experiments, Features, and Enablers. | Outcomes, Outputs, Measurements, and Value. | falsch | Incorrect. Those are steps in the outcome-driven cycle, not work items. | Prototypes, Experiments, Features, and Enablers. | Correct. Teams are free to use more work items, but these four are the recommended minimum for managing work on the pipeline. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0028
29 | quiz:scaledagile/ai-native-safe-overview/final/029 | Lesson 5: Development and Innovation at Scale | Which AI Governance pillar tracks token growth, sets usage caps, and attributes consumption costs to teams and products? | Controlling AI Spend | RICHTIG | Correct. AI spend scales with adoption because pricing is usage-based. This pillar tracks consumption growth, sets caps and alerts, and attributes costs clearly. | Enforcing Responsible AI | falsch | Incorrect. That pillar covers ethical, transparent, and compliant use. Cost tracking belongs to Controlling AI Spend. | Monitoring Agentic Behaviors | falsch | Incorrect. That pillar gives visibility into what autonomous agents do. Cost tracking belongs to Controlling AI Spend. | Managing and Exploiting AI Risks | falsch | Incorrect. That pillar manages the portfolio's risk posture. Cost tracking belongs to Controlling AI Spend. | Controlling AI Spend | Correct. AI spend scales with adoption because pricing is usage-based. This pillar tracks consumption growth, sets caps and alerts, and attributes costs clearly. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0029
30 | quiz:scaledagile/ai-native-safe-overview/final/030 | Lesson 5: Development and Innovation at Scale | What is the foundation that the four AI Governance pillars stand on? | AI Ethics | RICHTIG | Correct. AI Ethics covers the values an organization holds itself to beyond legal requirements. Regulation asks whether something violates the law, and ethics asks whether it disrespects or exploits human beings. | Legal compliance | falsch | Incorrect. Compliance is the regulatory minimum. The ethical foundation goes beyond what the law requires. | Shared platforms | falsch | Incorrect. Shared platforms belong to the AI Innovation Pipeline. The governance pillars stand on AI Ethics. | The investment strategy | falsch | Incorrect. Investment strategy is part of portfolio strategy. The governance pillars stand on AI Ethics. | AI Ethics | Correct. AI Ethics covers the values an organization holds itself to beyond legal requirements. Regulation asks whether something violates the law, and ethics asks whether it disrespects or exploits human beings. | confirmed | src:2026-08-26/upgrade-path-final-quiz#b0030

## Antwortoptionen
Nr | Frage-ID | Lektion | Frage | Option | Antworttext | Richtig? | Begründung
1 | quiz:scaledagile/ai-native-safe-overview/final/001 | Lesson 1: AI-Native SAFe Overview | Which four shifts define the AI-Native upgrade to SAFe? | A | Full Automation of Delivery; Autonomous AI-Only Teams; Longer and More Stable Planning Cadences; Centralized Innovation Labs. | falsch | Incorrect. AI-Native SAFe keeps humans in the loop, keeps teams cross-functional and human-led, shortens cadences, and spreads innovation across the organization rather than centralizing it.
1 | quiz:scaledagile/ai-native-safe-overview/final/001 | Lesson 1: AI-Native SAFe Overview | Which four shifts define the AI-Native upgrade to SAFe? | B | Focus on Outputs and Velocity; Specialist Silo Teams with AI Support; Annual Learning and Improvement Reviews; Innovation Restricted to Research and Development. | falsch | Incorrect. This is the opposite direction on every count: the shifts move away from output-centric management, silos, slow learning loops, and gatekept innovation.
1 | quiz:scaledagile/ai-native-safe-overview/final/001 | Lesson 1: AI-Native SAFe Overview | Which four shifts define the AI-Native upgrade to SAFe? | C | Optimized for Outcome-Driven Flow; Cross-Functional, AI-Augmented Teams; Iterative Learning and Rapid Experimentation Cycles; Development and Innovation at Scale. | RICHTIG | Correct. These four shifts amplify the core Lean-Agile practices: outcomes gain intent, teams become AI-augmented, learning cycles gain rapid experimentation, and development at scale gains innovation at scale.
1 | quiz:scaledagile/ai-native-safe-overview/final/001 | Lesson 1: AI-Native SAFe Overview | Which four shifts define the AI-Native upgrade to SAFe? | D | Prompt Engineering; Model Selection and Fine-Tuning; Token Economics; Agent Orchestration; Inference Cost Management. | falsch | Incorrect. These are AI techniques, not organizational shifts. The four shifts to become AI-Native describe how the operating model changes, not which tools get used.
2 | quiz:scaledagile/ai-native-safe-overview/final/002 | Lesson 2: Optimized for Outcome-Driven Flow | With AI, a team triples its feature output this quarter. When is that work actually “done”? | A | When every one of the features has shipped all the way to production. | falsch | Incorrect. Shipping is an output event. With no evidence of changed customer or business value, an organization can optimize ever faster for the wrong thing.
2 | quiz:scaledagile/ai-native-safe-overview/final/002 | Lesson 2: Optimized for Outcome-Driven Flow | With AI, a team triples its feature output this quarter. When is that work actually “done”? | B | When customer and business impact is validated and the learning is captured. | RICHTIG | Correct. AI removes the constraint on producing outputs, so shipping volume stops being the measure. Work is done when there is evidence the outcome moved, and the learning from that evidence is captured.
2 | quiz:scaledagile/ai-native-safe-overview/final/002 | Lesson 2: Optimized for Outcome-Driven Flow | With AI, a team triples its feature output this quarter. When is that work actually “done”? | C | When the AI-generated code passes all of the automated tests and reviews. | falsch | Incorrect. Passing tests confirms the output works as specified: it says nothing about whether the work created the change in value it was meant to create.
2 | quiz:scaledagile/ai-native-safe-overview/final/002 | Lesson 2: Optimized for Outcome-Driven Flow | With AI, a team triples its feature output this quarter. When is that work actually “done”? | D | When the team's velocity target is met and the burn-down chart reaches zero. | falsch | Incorrect. Velocity and burn-down measure volume delivered: exactly the output-driven measures that lose meaning once producing more is easy.
3 | quiz:scaledagile/ai-native-safe-overview/final/003 | Lesson 5: Development and Innovation at Scale | A prompt tells an AI agent exactly what to build and how, yet the agent's proposals keep missing the point and ignoring organizational standards. Which pillars of direction are missing? | A | Specifications: the prompt simply needs more technical detail about what and how. | falsch | Incorrect. The what and how are already covered. More technical detail can't tell the agent why the work matters or which organizational standards apply: those are the intent and context pillars.
3 | quiz:scaledagile/ai-native-safe-overview/final/003 | Lesson 5: Development and Innovation at Scale | A prompt tells an AI agent exactly what to build and how, yet the agent's proposals keep missing the point and ignoring organizational standards. Which pillars of direction are missing? | B | Access: the agent needs the permissions to deploy directly to production. | falsch | Incorrect. Deployment permissions don't help an agent understand why work exists or where it must fit, and keeping humans in the validation loop is a feature, not a limitation.
3 | quiz:scaledagile/ai-native-safe-overview/final/003 | Lesson 5: Development and Innovation at Scale | A prompt tells an AI agent exactly what to build and how, yet the agent's proposals keep missing the point and ignoring organizational standards. Which pillars of direction are missing? | C | Intent (the why) and context (the organizational reality the work must fit). | RICHTIG | Correct. Directing AI reliably takes all three pillars connected: intent (why), specifications (what and how), and context (where). This prompt covers only specifications: without intent and context, the agent can't aim at the change being sought or fit the organization's standards.
3 | quiz:scaledagile/ai-native-safe-overview/final/003 | Lesson 5: Development and Innovation at Scale | A prompt tells an AI agent exactly what to build and how, yet the agent's proposals keep missing the point and ignoring organizational standards. Which pillars of direction are missing? | D | Nothing is missing: the agent just needs a more capable underlying model. | falsch | Incorrect. A stronger model still can't infer the purpose behind the work or the organization's standards from a prompt that never provides them.
4 | quiz:scaledagile/ai-native-safe-overview/final/004 | Lesson 3: Cross-Functional, AI-Augmented Teams | An AI-Native team gathers to decide together how it will split an upcoming outcome between its humans and its AI agents. In the team's Align-Sense-Respond rhythm, which interaction is that? | A | Sense: the team is gathering new information about its own workload and capacity. | falsch | Incorrect. Sense is the deliberate gathering and analysis of feedback and learning from multiple sources. This scenario is a decision being made, not feedback being analyzed.
4 | quiz:scaledagile/ai-native-safe-overview/final/004 | Lesson 3: Cross-Functional, AI-Augmented Teams | An AI-Native team gathers to decide together how it will split an upcoming outcome between its humans and its AI agents. In the team's Align-Sense-Respond rhythm, which interaction is that? | B | Respond: any change to how the work is divided counts as a response. | falsch | Incorrect. Respond is the adjustment a team makes to workflows and products after sensing something. Here nothing was sensed: the team is making a forward-looking key decision, which is Align.
4 | quiz:scaledagile/ai-native-safe-overview/final/004 | Lesson 3: Cross-Functional, AI-Augmented Teams | An AI-Native team gathers to decide together how it will split an upcoming outcome between its humans and its AI agents. In the team's Align-Sense-Respond rhythm, which interaction is that? | C | None of them: staffing decisions sit outside the team rhythm. | falsch | Incorrect. Deciding how humans and AI agents share the work is central to how an AI-Native team operates: it's a textbook Align moment.
4 | quiz:scaledagile/ai-native-safe-overview/final/004 | Lesson 3: Cross-Functional, AI-Augmented Teams | An AI-Native team gathers to decide together how it will split an upcoming outcome between its humans and its AI agents. In the team's Align-Sense-Respond rhythm, which interaction is that? | D | Align: a key decision made together that moves the team toward the outcome. | RICHTIG | Correct. Align is where the team makes key decisions together so everyone, human and AI, moves in the same direction toward the outcome. Deciding how to split the work is exactly such a decision.
5 | quiz:scaledagile/ai-native-safe-overview/final/005 | Lesson 3: Cross-Functional, AI-Augmented Teams | You're forming a new AI-Native team. What's the right way to describe what the team needs? | A | By headcount: AI-Native teams should be as large as possible to absorb AI's extra output. | falsch | Incorrect. The direction is the opposite: teams get smaller and nimbler because AI collaboration lets fewer people cover more capability.
5 | quiz:scaledagile/ai-native-safe-overview/final/005 | Lesson 3: Cross-Functional, AI-Augmented Teams | You're forming a new AI-Native team. What's the right way to describe what the team needs? | B | By traditional role titles: one developer, one tester, one analyst, one designer per seat. | falsch | Incorrect. Fixed role-per-seat staffing is what the capability model replaces. Describing teams through the Product, Builder, Domain Expert, and AI capabilities keeps them small and flexible as AI absorbs more of the execution work.
5 | quiz:scaledagile/ai-native-safe-overview/final/005 | Lesson 3: Cross-Functional, AI-Augmented Teams | You're forming a new AI-Native team. What's the right way to describe what the team needs? | C | By its four core capabilities: Product, Builder, Domain Expert, and AI. | RICHTIG | Correct. AI-Native teams are smaller, nimbler, and described through capabilities rather than fixed role titles: Product anchors the team in customer needs, Builder turns outcomes into working solutions, the Domain Expert makes solutions fit the organization, and AI provides data and automation at speed.
5 | quiz:scaledagile/ai-native-safe-overview/final/005 | Lesson 3: Cross-Functional, AI-Augmented Teams | You're forming a new AI-Native team. What's the right way to describe what the team needs? | D | By AI agents first: humans are added only where agents fall short. | falsch | Incorrect. AI augments professionals rather than replacing them. Teams stay human-led: humans own the strategy, judgment, and domain expertise that direct what AI produces.
6 | quiz:scaledagile/ai-native-safe-overview/final/006 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | AI compresses parts of the Plan-Do-Check-Adjust learning cycle. Which parts shrink, and what do teams do with the time they gain? | A | Plan and Adjust shrink: AI makes planning largely unnecessary, so teams simply build continuously. | falsch | Incorrect. It's the reverse: Plan and Adjust gain time and importance. AI speeds up doing and checking, which makes deliberate human planning and adaptive decisions more valuable, not less.
6 | quiz:scaledagile/ai-native-safe-overview/final/006 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | AI compresses parts of the Plan-Do-Check-Adjust learning cycle. Which parts shrink, and what do teams do with the time they gain? | B | Do and Check shrink: teams reinvest the time in planning, adaptive decisions, and experiments. | RICHTIG | Correct. AI accelerates execution (Do) and validation (Check), so cadences compress and experimentation accelerates: teams spend the recovered time on Plan and Adjust, where human judgment matters most, and let evidence decide what happens next.
6 | quiz:scaledagile/ai-native-safe-overview/final/006 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | AI compresses parts of the Plan-Do-Check-Adjust learning cycle. Which parts shrink, and what do teams do with the time they gain? | C | None of them shrink: AI adds review overhead that lengthens every phase of the cycle. | falsch | Incorrect. Human validation stays in the loop, but the net effect of AI is dramatically faster Do and Check phases: that's what makes rapid experimentation cycles possible.
6 | quiz:scaledagile/ai-native-safe-overview/final/006 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | AI compresses parts of the Plan-Do-Check-Adjust learning cycle. Which parts shrink, and what do teams do with the time they gain? | D | All four phases shrink equally, so the cadences stay in the same proportion as before. | falsch | Incorrect. The compression is uneven: AI shortens Do and Check specifically, which is what frees teams to shift their attention toward Plan and Adjust.
7 | quiz:scaledagile/ai-native-safe-overview/final/007 | Lesson 5: Development and Innovation at Scale | When AI makes everyone in the organization a potential innovator, what keeps that innovation scalable and safe? | A | Restricting AI-powered building to the IT department, where it can be properly controlled. | falsch | Incorrect. Gatekeeping innovation back into one department gives up the shift's whole benefit. The answer to broad innovation is enablement with guardrails, not restriction.
7 | quiz:scaledagile/ai-native-safe-overview/final/007 | Lesson 5: Development and Innovation at Scale | When AI makes everyone in the organization a potential innovator, what keeps that innovation scalable and safe? | B | Nothing: guardrails would only slow innovation down, defeating the whole purpose. | falsch | Incorrect. Ungoverned AI solutions create fragile systems and technical debt. Guidelines and governance are what let innovation scale safely: they're the enabler, not the brake.
7 | quiz:scaledagile/ai-native-safe-overview/final/007 | Lesson 5: Development and Innovation at Scale | When AI makes everyone in the organization a potential innovator, what keeps that innovation scalable and safe? | C | Clear guidelines, shared AI infrastructure, and governance against fragile solutions. | RICHTIG | Correct. When employees across every department start building AI-powered tools, guidelines, shared infrastructure, and governance are what keep that innovation scalable, maintainable, and safe: without them, ungoverned solutions create fragile systems and technical debt.
7 | quiz:scaledagile/ai-native-safe-overview/final/007 | Lesson 5: Development and Innovation at Scale | When AI makes everyone in the organization a potential innovator, what keeps that innovation scalable and safe? | D | A freeze on new AI tools until every existing solution is fully documented and audited. | falsch | Incorrect. A freeze halts the innovation the shift exists to unlock. Scalability comes from guidelines, shared infrastructure, and governance operating alongside innovation, not ahead of it.
8 | quiz:scaledagile/ai-native-safe-overview/final/008 | Lesson 1: AI-Native SAFe Overview | What does the AI-Native Professional combine? | A | Technical AI skills, fully replacing the human skills that AI has now commoditized. | falsch | Incorrect. AI commoditizes execution, not human skills. As it does, context, empathy, ethics, judgment, and strategy become more valuable, not less.
8 | quiz:scaledagile/ai-native-safe-overview/final/008 | Lesson 1: AI-Native SAFe Overview | What does the AI-Native Professional combine? | B | AI fluency (directing and evaluating AI) with human context, empathy, judgment, and strategy. | RICHTIG | Correct. The AI-Native Professional lives in the overlap of the two domains: AI handles tasks that don't require human judgment, and the professional directs the AI, not just its output, while applying the human skills that have become the organization's most important asset.
8 | quiz:scaledagile/ai-native-safe-overview/final/008 | Lesson 1: AI-Native SAFe Overview | What does the AI-Native Professional combine? | C | Deep expertise in one AI tool combined with certification in the organization's compliance standards. | falsch | Incorrect. Tools keep changing: what endures is AI fluency, knowing how to direct whatever AI comes next, paired with the human skills AI cannot supply.
8 | quiz:scaledagile/ai-native-safe-overview/final/008 | Lesson 1: AI-Native SAFe Overview | What does the AI-Native Professional combine? | D | Prompt-writing speed with the ability to approve AI output quickly enough to keep up the pace. | falsch | Incorrect. Approving output quickly is the opposite of the role: the AI-Native Professional critically evaluates AI output and stays accountable for it.
9 | quiz:scaledagile/ai-native-safe-overview/final/009 | Lesson 1: AI-Native SAFe Overview | Why is experimenting with AI no longer enough for an organization? | A | Experiments are too expensive to run at today's model prices. | falsch | Incorrect. Cost is not the reason. The problem is that isolated experiments do not change how the organization works.
9 | quiz:scaledagile/ai-native-safe-overview/final/009 | Lesson 1: AI-Native SAFe Overview | Why is experimenting with AI no longer enough for an organization? | B | Becoming AI-Native is a whole-organization way of working, not a set of pilots. | RICHTIG | Correct. The pace and scale of change demand more than isolated experiments. Unlocking value from AI takes a unified, organization-wide approach.
9 | quiz:scaledagile/ai-native-safe-overview/final/009 | Lesson 1: AI-Native SAFe Overview | Why is experimenting with AI no longer enough for an organization? | C | Most AI experiments fail for technical reasons. | falsch | Incorrect. The technology usually works. The gap is organizational, not technical.
9 | quiz:scaledagile/ai-native-safe-overview/final/009 | Lesson 1: AI-Native SAFe Overview | Why is experimenting with AI no longer enough for an organization? | D | Regulators now require organizations to move past the experimental stage. | falsch | Incorrect. No regulation drives this. The driver is the need to unlock real value from AI across the whole organization.
10 | quiz:scaledagile/ai-native-safe-overview/final/010 | Lesson 1: AI-Native SAFe Overview | What does AI-Native SAFe provide to help organizations get a return from AI? | A | A catalog of approved AI tools and vendors. | falsch | Incorrect. AI-Native SAFe is an operating model, not a tool list. Tools change quickly, but the roles and structures endure.
10 | quiz:scaledagile/ai-native-safe-overview/final/010 | Lesson 1: AI-Native SAFe Overview | What does AI-Native SAFe provide to help organizations get a return from AI? | B | The roles, processes, and structures needed to achieve a return from AI. | RICHTIG | Correct. Research found that the missing piece was a standard framework. AI-Native SAFe fills that gap with an outcome-driven operating model.
10 | quiz:scaledagile/ai-native-safe-overview/final/010 | Lesson 1: AI-Native SAFe Overview | What does AI-Native SAFe provide to help organizations get a return from AI? | C | A guarantee that AI investments will pay off within one year. | falsch | Incorrect. No framework can guarantee returns. AI-Native SAFe provides the structure that makes returns achievable.
10 | quiz:scaledagile/ai-native-safe-overview/final/010 | Lesson 1: AI-Native SAFe Overview | What does AI-Native SAFe provide to help organizations get a return from AI? | D | A dedicated AI department that runs all AI work centrally. | falsch | Incorrect. AI-Native SAFe spreads AI capability across the whole organization instead of centralizing it in one department.
11 | quiz:scaledagile/ai-native-safe-overview/final/011 | Lesson 1: AI-Native SAFe Overview | Reviewing the AI-Native SAFe Big Picture, a colleague points to the portfolio level, where connected OKRs cascade from portfolio strategy and curated data keeps work at every level aligned to value. Which critical shift does this part of the Big Picture express? | A | Development at Scale to Development and Innovation at Scale | falsch | Incorrect. That shift is expressed by the AI Innovation Pipeline, whose shared platforms and embedded policies make innovation scalable across the organization.
11 | quiz:scaledagile/ai-native-safe-overview/final/011 | Lesson 1: AI-Native SAFe Overview | Reviewing the AI-Native SAFe Big Picture, a colleague points to the portfolio level, where connected OKRs cascade from portfolio strategy and curated data keeps work at every level aligned to value. Which critical shift does this part of the Big Picture express? | B | Optimized for Flow to Optimized for Outcome-Driven Flow | RICHTIG | Correct. Connected OKRs, portfolio strategy, and curated data are the outcome-driven elements of the Big Picture. They keep everything flowing through the system aligned to value instead of output volume.
11 | quiz:scaledagile/ai-native-safe-overview/final/011 | Lesson 1: AI-Native SAFe Overview | Reviewing the AI-Native SAFe Big Picture, a colleague points to the portfolio level, where connected OKRs cascade from portfolio strategy and curated data keeps work at every level aligned to value. Which critical shift does this part of the Big Picture express? | C | Iterative Learning Cycles to Iterative Learning and Rapid Experimentation Cycles | falsch | Incorrect. That shift appears in the cadenced events on the Big Picture, such as PI Outcome Planning and Sense and Respond, which shorten learning cycles across the ART.
11 | quiz:scaledagile/ai-native-safe-overview/final/011 | Lesson 1: AI-Native SAFe Overview | Reviewing the AI-Native SAFe Big Picture, a colleague points to the portfolio level, where connected OKRs cascade from portfolio strategy and curated data keeps work at every level aligned to value. Which critical shift does this part of the Big Picture express? | D | Cross-Functional Teams to Cross-Functional, AI-Augmented Teams | falsch | Incorrect. That shift is expressed by the AI-Native ARTs and AI-Native Teams, smaller teams described through Product, Builder, Domain Expert, and AI capabilities.
12 | quiz:scaledagile/ai-native-safe-overview/final/012 | Lesson 1: AI-Native SAFe Overview | In a human-centric AI culture, what becomes the organization's most important asset? | A | The size of its AI infrastructure budget. | falsch | Incorrect. Anyone can spend on infrastructure. The differentiator is the human judgment that directs what the AI produces.
12 | quiz:scaledagile/ai-native-safe-overview/final/012 | Lesson 1: AI-Native SAFe Overview | In a human-centric AI culture, what becomes the organization's most important asset? | B | Human skills such as creativity, empathy, and strategic decision-making. | RICHTIG | Correct. When AI handles the tasks that do not require human judgment, people are freed to direct outcomes. The ability to apply these human skills becomes the most important asset.
12 | quiz:scaledagile/ai-native-safe-overview/final/012 | Lesson 1: AI-Native SAFe Overview | In a human-centric AI culture, what becomes the organization's most important asset? | C | The number of AI agents deployed across its teams. | falsch | Incorrect. Agents are widely available. The value comes from the people who direct them well.
12 | quiz:scaledagile/ai-native-safe-overview/final/012 | Lesson 1: AI-Native SAFe Overview | In a human-centric AI culture, what becomes the organization's most important asset? | D | Exclusive contracts with the leading AI model providers. | falsch | Incorrect. Models are a commodity that any competitor can rent. Human skills are what cannot be copied.
13 | quiz:scaledagile/ai-native-safe-overview/final/013 | Lesson 2: Optimized for Outcome-Driven Flow | In the outcome-driven product development cycle, what do measurements show? | A | How many outputs each team produced during the PI. | falsch | Incorrect. Counting outputs is output-driven measurement. The cycle measures progress toward outcomes instead.
13 | quiz:scaledagile/ai-native-safe-overview/final/013 | Lesson 2: Optimized for Outcome-Driven Flow | In the outcome-driven product development cycle, what do measurements show? | B | Whether the outputs are making progress against the defined outcomes. | RICHTIG | Correct. Measurements provide the insight to change or keep the current plan. They connect the work back to the outcomes it was meant to move.
13 | quiz:scaledagile/ai-native-safe-overview/final/013 | Lesson 2: Optimized for Outcome-Driven Flow | In the outcome-driven product development cycle, what do measurements show? | C | Which teams are working the fastest. | falsch | Incorrect. Speed of production stopped being the constraint once AI removed the output bottleneck. The question is whether the work is moving the outcome.
13 | quiz:scaledagile/ai-native-safe-overview/final/013 | Lesson 2: Optimized for Outcome-Driven Flow | In the outcome-driven product development cycle, what do measurements show? | D | How much of the budget has been spent so far. | falsch | Incorrect. Spend tracking matters elsewhere, but measurements in this cycle show progress against outcomes.
14 | quiz:scaledagile/ai-native-safe-overview/final/014 | Lesson 2: Optimized for Outcome-Driven Flow | Why must Portfolio Leadership include the organization's AI spend in its investment strategy? | A | AI costs are usage-driven, and consumption at scale can outrun a fixed budget. | RICHTIG | Correct. Costs shift from fixed salaries and licenses to variable consumption. Agents are paid in tokens, so usage must be modeled and managed.
14 | quiz:scaledagile/ai-native-safe-overview/final/014 | Lesson 2: Optimized for Outcome-Driven Flow | Why must Portfolio Leadership include the organization's AI spend in its investment strategy? | B | AI vendors require an annual spending commitment before granting access. | falsch | Incorrect. Vendor terms are not the reason. The reason is that usage-driven costs behave differently from fixed costs.
14 | quiz:scaledagile/ai-native-safe-overview/final/014 | Lesson 2: Optimized for Outcome-Driven Flow | Why must Portfolio Leadership include the organization's AI spend in its investment strategy? | C | AI spend is small enough to hide inside existing license budgets. | falsch | Incorrect. The opposite is true. A capability that costs little in pilot can become a major line item at scale.
14 | quiz:scaledagile/ai-native-safe-overview/final/014 | Lesson 2: Optimized for Outcome-Driven Flow | Why must Portfolio Leadership include the organization's AI spend in its investment strategy? | D | Accounting rules require AI costs to be reported separately. | falsch | Incorrect. This is about investment strategy, not reporting rules. Usage-driven consumption changes how budgets must be planned.
15 | quiz:scaledagile/ai-native-safe-overview/final/015 | Lesson 2: Optimized for Outcome-Driven Flow | In AI-Native SAFe, where are OKRs used? | A | Only at the portfolio level, where strategy is set. | falsch | Incorrect. Portfolio OKRs alone leave teams disconnected from strategy. Every level writes outcomes relevant to its own work.
15 | quiz:scaledagile/ai-native-safe-overview/final/015 | Lesson 2: Optimized for Outcome-Driven Flow | In AI-Native SAFe, where are OKRs used? | B | Only at the team level, where the work gets done. | falsch | Incorrect. Team OKRs need portfolio and ART outcomes above them to cascade from. Otherwise teams pull in different directions.
15 | quiz:scaledagile/ai-native-safe-overview/final/015 | Lesson 2: Optimized for Outcome-Driven Flow | In AI-Native SAFe, where are OKRs used? | C | At every level, from portfolios to teams. | RICHTIG | Correct. AI-Native SAFe mandates OKRs at every level. Cascading outcomes keep ART and team work connected to strategy.
15 | quiz:scaledagile/ai-native-safe-overview/final/015 | Lesson 2: Optimized for Outcome-Driven Flow | In AI-Native SAFe, where are OKRs used? | D | OKRs are optional and each ART decides whether to use them. | falsch | Incorrect. AI-Native SAFe now mandates OKRs at every level. They are how daily work connects to overall strategy.
16 | quiz:scaledagile/ai-native-safe-overview/final/016 | Lesson 2: Optimized for Outcome-Driven Flow | What is curated data? | A | Enterprise information deliberately prepared for AI. | RICHTIG | Correct. Curated data enables reliable and unique insights. Without it, AI produces fragmented or conflicting results.
16 | quiz:scaledagile/ai-native-safe-overview/final/016 | Lesson 2: Optimized for Outcome-Driven Flow | What is curated data? | B | Any data an organization stores in a database. | falsch | Incorrect. Storage alone is not curation. The data must be deliberately prepared so AI can use it well.
16 | quiz:scaledagile/ai-native-safe-overview/final/016 | Lesson 2: Optimized for Outcome-Driven Flow | What is curated data? | C | Data that has been anonymized for privacy compliance. | falsch | Incorrect. Anonymization is a privacy technique. Curation is about preparing data so it produces reliable insights.
16 | quiz:scaledagile/ai-native-safe-overview/final/016 | Lesson 2: Optimized for Outcome-Driven Flow | What is curated data? | D | Public data purchased from third-party providers. | falsch | Incorrect. Purchased data is available to competitors too. Curated proprietary data is the advantage no one else can copy.
17 | quiz:scaledagile/ai-native-safe-overview/final/017 | Lesson 2: Optimized for Outcome-Driven Flow | Data has been successfully curated when it meets which conditions? | A | It is complete, accurate, well-maintained, securely accessible, and clearly owned. | RICHTIG | Correct. These five conditions are what turn proprietary data into reliable raw material for AI.
17 | quiz:scaledagile/ai-native-safe-overview/final/017 | Lesson 2: Optimized for Outcome-Driven Flow | Data has been successfully curated when it meets which conditions? | B | It is stored in a single central warehouse with one global owner. | falsch | Incorrect. Curation is about the quality and stewardship of the data, not where it lives. Owners must be identifiable, but not singular.
17 | quiz:scaledagile/ai-native-safe-overview/final/017 | Lesson 2: Optimized for Outcome-Driven Flow | Data has been successfully curated when it meets which conditions? | C | It is fully structured, with all documents converted into tables. | falsch | Incorrect. Curation extends beyond structured records. Documents and slide decks hold much of an organization's knowledge and are prepared for AI too.
17 | quiz:scaledagile/ai-native-safe-overview/final/017 | Lesson 2: Optimized for Outcome-Driven Flow | Data has been successfully curated when it meets which conditions? | D | It is encrypted, backed up, and retained for at least seven years. | falsch | Incorrect. Those are IT practices, not the curation conditions. Curated data must also be complete, accurate, maintained, accessible, and owned.
18 | quiz:scaledagile/ai-native-safe-overview/final/018 | Lesson 3: Cross-Functional, AI-Augmented Teams | Teams on an AI-Native ART can move faster than ever. Why does the ART still keep a regular cadence? | A | Cadence builds in time to reconcile local decisions and dependencies before they accumulate. | RICHTIG | Correct. Cadence gives the organization the structure to metabolize the learning coming from fast-moving teams. It balances rapid innovation with cadence-based learning.
18 | quiz:scaledagile/ai-native-safe-overview/final/018 | Lesson 3: Cross-Functional, AI-Augmented Teams | Teams on an AI-Native ART can move faster than ever. Why does the ART still keep a regular cadence? | B | Cadence slows the teams down to a pace leadership can supervise. | falsch | Incorrect. Cadence is not a brake. It provides the structure that lets work move at the speed of AI safely.
18 | quiz:scaledagile/ai-native-safe-overview/final/018 | Lesson 3: Cross-Functional, AI-Augmented Teams | Teams on an AI-Native ART can move faster than ever. Why does the ART still keep a regular cadence? | C | Cadence is kept only for tradition, since the events no longer serve a purpose. | falsch | Incorrect. The events matter more at AI speed, not less. They are where local decisions get reconciled.
18 | quiz:scaledagile/ai-native-safe-overview/final/018 | Lesson 3: Cross-Functional, AI-Augmented Teams | Teams on an AI-Native ART can move faster than ever. Why does the ART still keep a regular cadence? | D | Cadence gives AI agents fixed deadlines to work toward. | falsch | Incorrect. Cadence exists for human alignment and learning, not for agent scheduling.
19 | quiz:scaledagile/ai-native-safe-overview/final/019 | Lesson 3: Cross-Functional, AI-Augmented Teams | On an AI-Native Team, which capability brings the specialized customer and business context that makes solutions fit the organization? | A | Product | falsch | Incorrect. Product defines the vision and anchors the team in customer needs. The specialized domain context comes from the Domain Expert.
19 | quiz:scaledagile/ai-native-safe-overview/final/019 | Lesson 3: Cross-Functional, AI-Augmented Teams | On an AI-Native Team, which capability brings the specialized customer and business context that makes solutions fit the organization? | B | Builder | falsch | Incorrect. The Builder uses AI to turn outcomes into working solutions. The Domain Expert supplies the context those solutions must fit.
19 | quiz:scaledagile/ai-native-safe-overview/final/019 | Lesson 3: Cross-Functional, AI-Augmented Teams | On an AI-Native Team, which capability brings the specialized customer and business context that makes solutions fit the organization? | C | Domain Expert | RICHTIG | Correct. The Domain Expert brings deep customer, business, or regulatory knowledge. That context keeps solutions from staying generic.
19 | quiz:scaledagile/ai-native-safe-overview/final/019 | Lesson 3: Cross-Functional, AI-Augmented Teams | On an AI-Native Team, which capability brings the specialized customer and business context that makes solutions fit the organization? | D | AI | falsch | Incorrect. AI provides data and automation under human supervision. It cannot supply the organization's specialized business context.
20 | quiz:scaledagile/ai-native-safe-overview/final/020 | Lesson 3: Cross-Functional, AI-Augmented Teams | What is the “POC Graveyard”? | A | The archive where retired AI models are stored. | falsch | Incorrect. The term is about failed adoption, not model storage. It names the pile of demos that never became real products.
20 | quiz:scaledagile/ai-native-safe-overview/final/020 | Lesson 3: Cross-Functional, AI-Augmented Teams | What is the “POC Graveyard”? | B | Promising AI demonstrations that never reach scaled, sustained use. | RICHTIG | Correct. Most AI initiatives fail because no one owned the path from prototype to production. The AI Value Architect exists to fill that gap.
20 | quiz:scaledagile/ai-native-safe-overview/final/020 | Lesson 3: Cross-Functional, AI-Augmented Teams | What is the “POC Graveyard”? | C | A list of AI vendors that went out of business. | falsch | Incorrect. The graveyard is inside organizations, not the vendor market. It holds proofs of concept that never scaled.
20 | quiz:scaledagile/ai-native-safe-overview/final/020 | Lesson 3: Cross-Functional, AI-Augmented Teams | What is the “POC Graveyard”? | D | The backlog of AI ideas a team has not started yet. | falsch | Incorrect. These initiatives were started and even demonstrated. They died on the way from prototype to production.
21 | quiz:scaledagile/ai-native-safe-overview/final/021 | Lesson 3: Cross-Functional, AI-Augmented Teams | Who is well positioned to become an AI Value Architect? | A | Outside specialists hired specifically for the role. | falsch | Incorrect. The AI Value Architect is not a new specialist hired from outside. It grows from existing roles.
21 | quiz:scaledagile/ai-native-safe-overview/final/021 | Lesson 3: Cross-Functional, AI-Augmented Teams | Who is well positioned to become an AI Value Architect? | B | Systems thinkers and coaches the organization already has, such as Scrum Masters, RTEs, and Architects. | RICHTIG | Correct. The role grows out of roles SAFe already has. People who already coach and hold the systems view can add AI fluency and step in.
21 | quiz:scaledagile/ai-native-safe-overview/final/021 | Lesson 3: Cross-Functional, AI-Augmented Teams | Who is well positioned to become an AI Value Architect? | C | The most senior AI engineer on each team. | falsch | Incorrect. Technical depth alone is not the qualification. The role needs coaching skill and a systems view across the ART.
21 | quiz:scaledagile/ai-native-safe-overview/final/021 | Lesson 3: Cross-Functional, AI-Augmented Teams | Who is well positioned to become an AI Value Architect? | D | Any volunteer, since the role needs no particular background. | falsch | Incorrect. The role draws on coaching experience and systems thinking. That is why existing SAFe roles are the natural candidates.
22 | quiz:scaledagile/ai-native-safe-overview/final/022 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What makes a product vision compelling in AI-Native SAFe? | A | It is informed by data, aligned with strategy, and anchored to architectural foundations. | RICHTIG | Correct. These three characteristics identify a compelling vision. A clear vision lets teams and AI agents make local decisions aligned to the long-term trajectory.
22 | quiz:scaledagile/ai-native-safe-overview/final/022 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What makes a product vision compelling in AI-Native SAFe? | B | It is ambitious enough that no competitor could promise the same. | falsch | Incorrect. Ambition alone is not the test. The vision also needs data, strategy alignment, and architectural grounding.
22 | quiz:scaledagile/ai-native-safe-overview/final/022 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What makes a product vision compelling in AI-Native SAFe? | C | It is written by leadership and kept stable for at least three years. | falsch | Incorrect. Who writes it and how long it lasts are not the defining traits. The three characteristics are data, strategy, and architecture.
22 | quiz:scaledagile/ai-native-safe-overview/final/022 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What makes a product vision compelling in AI-Native SAFe? | D | It lists every feature the ART plans to build. | falsch | Incorrect. A feature list is a roadmap artifact, and an output-driven one at that. The vision defines the mission and long-term goals.
23 | quiz:scaledagile/ai-native-safe-overview/final/023 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | On the Outcome-Driven Roadmap, what is a “moonshot”? | A | A milestone with an immovable external date. | falsch | Incorrect. That describes a fixed-date milestone. A moonshot is an outcome, not a milestone.
23 | quiz:scaledagile/ai-native-safe-overview/final/023 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | On the Outcome-Driven Roadmap, what is a “moonshot”? | B | A bold, aspirational outcome that prioritizes innovation. | RICHTIG | Correct. A moonshot is a bold aspiration in its own outcome swimlane. Roofshots are the outcomes used to predictably optimize or iterate a product.
23 | quiz:scaledagile/ai-native-safe-overview/final/023 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | On the Outcome-Driven Roadmap, what is a “moonshot”? | C | An outcome used to predictably optimize an existing product. | falsch | Incorrect. That is a roofshot. Moonshots prioritize innovation over predictability.
23 | quiz:scaledagile/ai-native-safe-overview/final/023 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | On the Outcome-Driven Roadmap, what is a “moonshot”? | D | A release that reaches customers ahead of schedule. | falsch | Incorrect. Releases mark when value reaches customers. A moonshot is a type of ART outcome on the roadmap.
24 | quiz:scaledagile/ai-native-safe-overview/final/024 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What is the most significant logistical change in PI Outcome Planning compared to traditional PI Planning? | A | Only team leads attend, to keep the event small. | falsch | Incorrect. The entire ART attends. The change is the length, not the attendance.
24 | quiz:scaledagile/ai-native-safe-overview/final/024 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What is the most significant logistical change in PI Outcome Planning compared to traditional PI Planning? | B | The event is accomplished in a single day. | RICHTIG | Correct. PI Outcome Planning is a one-day event held at the start of every PI. The entire AI-Native ART attends.
24 | quiz:scaledagile/ai-native-safe-overview/final/024 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What is the most significant logistical change in PI Outcome Planning compared to traditional PI Planning? | C | The event is fully asynchronous, with no live sessions. | falsch | Incorrect. It is a live, facilitated day with breakouts, reviews, and a confidence vote.
24 | quiz:scaledagile/ai-native-safe-overview/final/024 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | What is the most significant logistical change in PI Outcome Planning compared to traditional PI Planning? | D | It happens once a year instead of every PI. | falsch | Incorrect. It happens at the start of every PI. What changed is that it now fits in one day.
25 | quiz:scaledagile/ai-native-safe-overview/final/025 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Which two SAFe events does the Sense and Respond event replace? | A | PI Planning and the Solution Demo. | falsch | Incorrect. PI-level planning becomes PI Outcome Planning, a separate event. Sense and Respond replaces Inspect and Adapt and the System Demo.
25 | quiz:scaledagile/ai-native-safe-overview/final/025 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Which two SAFe events does the Sense and Respond event replace? | B | Inspect and Adapt and the System Demo. | RICHTIG | Correct. Sense and Respond is a two-hour event at each iteration boundary. The first hour senses what happened, and the second hour decides what changes.
25 | quiz:scaledagile/ai-native-safe-overview/final/025 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Which two SAFe events does the Sense and Respond event replace? | C | The Daily Stand-up and the Iteration Review. | falsch | Incorrect. Team-level rhythms continue through Align, Sense, Respond. The ART-level event replaces Inspect and Adapt and the System Demo.
25 | quiz:scaledagile/ai-native-safe-overview/final/025 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Which two SAFe events does the Sense and Respond event replace? | D | Backlog Refinement and the Iteration Retrospective. | falsch | Incorrect. Those team practices are not what changed. Sense and Respond replaces the two ART-level learning events.
26 | quiz:scaledagile/ai-native-safe-overview/final/026 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Early in development, a team wants honest reactions to a prototype from a small group of real customers. Which demo fits? | A | A personal, learning demo, such as a hand-picked focus group. | RICHTIG | Correct. This is the Test Hypotheses Before Scaling quadrant. Small audiences allow deeper interactions and repeated demos with the same group.
26 | quiz:scaledagile/ai-native-safe-overview/final/026 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Early in development, a team wants honest reactions to a prototype from a small group of real customers. Which demo fits? | B | A broadcast, persuading demo, such as a launch event. | falsch | Incorrect. Launch events generate broad demand. That comes after the team has learned what works.
26 | quiz:scaledagile/ai-native-safe-overview/final/026 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Early in development, a team wants honest reactions to a prototype from a small group of real customers. Which demo fits? | C | A personal, persuading demo for the biggest customer. | falsch | Incorrect. Persuading assumes the solution already works as intended. The team is still learning.
26 | quiz:scaledagile/ai-native-safe-overview/final/026 | Lesson 4: Iterative Learning and Rapid Experimentation Cycles | Early in development, a team wants honest reactions to a prototype from a small group of real customers. Which demo fits? | D | A broadcast, learning demo through self-guided product access. | falsch | Incorrect. Broadcast learning suits products already tested with a smaller group. This prototype has not reached that stage.
27 | quiz:scaledagile/ai-native-safe-overview/final/027 | Lesson 5: Development and Innovation at Scale | AI-Native SAFe defines two types of specifications. What are they? | A | Functionality specifications and policy specifications. | RICHTIG | Correct. Functionality specifications describe the intended implementation. Policy specifications set the limits the Builders must stay within.
27 | quiz:scaledagile/ai-native-safe-overview/final/027 | Lesson 5: Development and Innovation at Scale | AI-Native SAFe defines two types of specifications. What are they? | B | Technical specifications and business specifications. | falsch | Incorrect. The split is not technical versus business. It is what to build versus the limits to build within.
27 | quiz:scaledagile/ai-native-safe-overview/final/027 | Lesson 5: Development and Innovation at Scale | AI-Native SAFe defines two types of specifications. What are they? | C | Draft specifications and approved specifications. | falsch | Incorrect. Approval status is not the distinction. The two types are functionality and policy.
27 | quiz:scaledagile/ai-native-safe-overview/final/027 | Lesson 5: Development and Innovation at Scale | AI-Native SAFe defines two types of specifications. What are they? | D | Human specifications and agent specifications. | falsch | Incorrect. Specifications serve people and agents alike. The two types are functionality and policy.
28 | quiz:scaledagile/ai-native-safe-overview/final/028 | Lesson 5: Development and Innovation at Scale | Which four work items does AI-Native SAFe recommend at a minimum on the AI Innovation Pipeline? | A | Epics, Capabilities, Features, and Stories. | falsch | Incorrect. That is the traditional SAFe requirements hierarchy. The pipeline's recommended set is Prototypes, Experiments, Features, and Enablers.
28 | quiz:scaledagile/ai-native-safe-overview/final/028 | Lesson 5: Development and Innovation at Scale | Which four work items does AI-Native SAFe recommend at a minimum on the AI Innovation Pipeline? | B | Prototypes, Experiments, Features, and Enablers. | RICHTIG | Correct. Teams are free to use more work items, but these four are the recommended minimum for managing work on the pipeline.
28 | quiz:scaledagile/ai-native-safe-overview/final/028 | Lesson 5: Development and Innovation at Scale | Which four work items does AI-Native SAFe recommend at a minimum on the AI Innovation Pipeline? | C | Tasks, Bugs, Spikes, and Releases. | falsch | Incorrect. Those are day-to-day tracking items. The recommended pipeline set is Prototypes, Experiments, Features, and Enablers.
28 | quiz:scaledagile/ai-native-safe-overview/final/028 | Lesson 5: Development and Innovation at Scale | Which four work items does AI-Native SAFe recommend at a minimum on the AI Innovation Pipeline? | D | Outcomes, Outputs, Measurements, and Value. | falsch | Incorrect. Those are steps in the outcome-driven cycle, not work items.
29 | quiz:scaledagile/ai-native-safe-overview/final/029 | Lesson 5: Development and Innovation at Scale | Which AI Governance pillar tracks token growth, sets usage caps, and attributes consumption costs to teams and products? | A | Controlling AI Spend | RICHTIG | Correct. AI spend scales with adoption because pricing is usage-based. This pillar tracks consumption growth, sets caps and alerts, and attributes costs clearly.
29 | quiz:scaledagile/ai-native-safe-overview/final/029 | Lesson 5: Development and Innovation at Scale | Which AI Governance pillar tracks token growth, sets usage caps, and attributes consumption costs to teams and products? | B | Enforcing Responsible AI | falsch | Incorrect. That pillar covers ethical, transparent, and compliant use. Cost tracking belongs to Controlling AI Spend.
29 | quiz:scaledagile/ai-native-safe-overview/final/029 | Lesson 5: Development and Innovation at Scale | Which AI Governance pillar tracks token growth, sets usage caps, and attributes consumption costs to teams and products? | C | Monitoring Agentic Behaviors | falsch | Incorrect. That pillar gives visibility into what autonomous agents do. Cost tracking belongs to Controlling AI Spend.
29 | quiz:scaledagile/ai-native-safe-overview/final/029 | Lesson 5: Development and Innovation at Scale | Which AI Governance pillar tracks token growth, sets usage caps, and attributes consumption costs to teams and products? | D | Managing and Exploiting AI Risks | falsch | Incorrect. That pillar manages the portfolio's risk posture. Cost tracking belongs to Controlling AI Spend.
30 | quiz:scaledagile/ai-native-safe-overview/final/030 | Lesson 5: Development and Innovation at Scale | What is the foundation that the four AI Governance pillars stand on? | A | AI Ethics | RICHTIG | Correct. AI Ethics covers the values an organization holds itself to beyond legal requirements. Regulation asks whether something violates the law, and ethics asks whether it disrespects or exploits human beings.
30 | quiz:scaledagile/ai-native-safe-overview/final/030 | Lesson 5: Development and Innovation at Scale | What is the foundation that the four AI Governance pillars stand on? | B | Legal compliance | falsch | Incorrect. Compliance is the regulatory minimum. The ethical foundation goes beyond what the law requires.
30 | quiz:scaledagile/ai-native-safe-overview/final/030 | Lesson 5: Development and Innovation at Scale | What is the foundation that the four AI Governance pillars stand on? | C | Shared platforms | falsch | Incorrect. Shared platforms belong to the AI Innovation Pipeline. The governance pillars stand on AI Ethics.
30 | quiz:scaledagile/ai-native-safe-overview/final/030 | Lesson 5: Development and Innovation at Scale | What is the foundation that the four AI Governance pillars stand on? | D | The investment strategy | falsch | Incorrect. Investment strategy is part of portfolio strategy. The governance pillars stand on AI Ethics.

## Info
AI-Native SAFe Overview — Final Quiz
Fragen im Pool | 30
Antwortoptionen je Frage | 4
Fragen pro Versuch | 15
Bestehensgrenze | 12 von 15 (80 %)
Modus | Open Book, unbegrenzte Wiederholungen, ohne Zeitlimit
Blatt „Fragen“ | Eine Zeile je Frage, alle Optionen nebeneinander.
Blatt „Antwortoptionen“ | Eine Zeile je Antwortoption — zum Filtern und Sortieren.
Quelle | src:2026-08-26/upgrade-path-final-quiz
Herkunft | Bundle-Chunk FinalQuiz-DUvUYCnK.js der Upgrade-Path-Webanwendung
Vorbehalt | Das Original-Artefakt wurde nach dem Auslesen neu deployt; die Transkription ist nicht byte-verifiziert. Siehe source.yaml.
Rechte | Scaled Agile, Inc. — keine Weitergabe (rights.redistribution: none)